## README + Dashboard
County Captain Recruitment Tracker
GA County Town Halls 2026 · Datos Lab · Maria Palacios, Executive Director
HOW TO USE THIS WORKBOOK
1. The Captains tab is the working list. One row per person you are recruiting to lead a county. Update weekly.
2. The Counties tab is the strategic frame. One row per priority county; shows whether each has a captain locked, the target legislator, and the planned town hall date.
3. The Funnel tab tracks each captain through 6 stages (Identified, Contacted, 1:1 done, Trained, Committed, Hosting). Pivot of the Captains tab.
4. The Pipeline by Stage tab is a visual dashboard for coalition leadership meetings.
5. The Onboarding tab is the captain commitment + role description; print 1 per signed captain.
6. The Decision Log tab captures every coalition decision: who decided, what the dissent was, what was the trade-off.
7. Pale blue cells are fillable. Dropdowns are provided where useful. Do not change column headers; the formulas reference them.
HEADLINE METRICS (live, from Captains + Counties tabs)
Counties on our priority list
Counties with a committed captain
Captains identified (any stage)
Captains who have completed 1:1
Captains trained
Captains hosting (town hall locked)
Town halls scheduled (Counties)
% of priority counties covered
WHAT WE ARE FIGHTING FOR
Louisiana v. Callais could gut Section 2 of the Voting Rights Act. If it does, Georgia could lose 2 minority opportunity congressional districts (current 5 to 9 D-R delegation could become 3 to 11) and the GA legislature could lose minority-VAP seats. Across the South, an estimated 191 state legislative seats are at risk. Our affirmative answer: pass the Georgia Voting Rights Act of 2026 (a state-level Section 2) and hold every state legislator publicly accountable. County captains are how we organize that accountability one community at a time.

## Captains
Captains
One row per person. Stage 1=Identified, 2=Contacted, 3=1:1 done, 4=Trained, 5=Committed, 6=Hosting.
ID | Name | County | Phone | Email | Constituency / community | Identified by | Stage (1 to 6) | Stage label | 1:1 date | Trained on | Committed on | Town hall date | Capacity (hrs/wk) | Notes / next step | Last updated
1 | Aunjanue Mosley | Gwinnett | (404) 555-0151 | amosley@example.org | Black women, faith leaders | Maria Palacios | 5 |  | 2026-04-12 | 2026-04-26 | 2026-05-04 | 2026-06-06 | 8 | Wants co-captain to share load; consider pairing with Pastor Reed. | 2026-05-01
2 | Pastor J. Reed | Gwinnett | (770) 555-0166 | preed@example.com | AME church coalition, seniors | Aunjanue Mosley | 4 |  | 2026-04-15 | 2026-04-26 |  |  | 6 | Concerned about Alinsky-style accountability sessions; wants story-led format. | 2026-05-01
3 | Linh Tran | Gwinnett | (678) 555-0112 | ltran@example.org | Vietnamese American voters | Linh Bui (AAAJ) | 3 |  | 2026-04-09 |  |  |  | 10 | Will commit if interpretation budget is locked. Confirm by 5/3. | 2026-05-01
4 | Carlos Mendez | Hall | (770) 555-0143 | cmendez@example.org | Latinx Gainesville organizers | GA Familias Unidas | 2 | [5 empty] | 6 | Texted; awaiting reply. Has organized 2 prior turnout events. | 2026-04-30
5 | DeMarcus Allen | Bibb | (478) 555-0188 | dallen@example.org | Mercer student org, Macon Black church | ACLU-GA | 4 |  | 2026-04-18 | 2026-04-26 |  |  | 12 | High capacity, strong story; ready to commit if we confirm venue. | 2026-05-01
6 | Rev. Sarah Womack | Chatham | (912) 555-0107 | swomack@example.com | Savannah Baptist coalition | NAACP-GA | 5 |  | 2026-04-05 | 2026-04-19 | 2026-04-25 | 2026-05-30 | 10 | Already booked Asbury Memorial. Needs sign-up volunteers. | 2026-05-01
7 | Kim Park | Cobb | (770) 555-0123 | kpark@example.org | Korean American, suburban moms | Linh Bui (AAAJ) | 3 |  | 2026-04-22 |  |  |  | 5 | Skeptical we can move Sen. Kirkpatrick; wants written commitment from coalition first. | 2026-05-01
8 | Tyrone Brooks Jr. | Fulton | (404) 555-0177 | tbrooks@example.org | South Fulton youth + LGBTQ | Maria Palacios | 6 |  | 2026-03-28 | 2026-04-12 | 2026-04-19 | 2026-05-16 | 15 | Town hall locked at South Fulton Arts Center. Press lead identified. | 2026-05-01
9 | Esperanza Rivera | Clayton | (404) 555-0189 | erivera@example.org | Latinx, public school parents | GA Familias Unidas | 2 | [5 empty] | 4 | Out of country until 5/15. Reschedule 1:1 for week of 5/18. | 2026-04-30
10 | Imam Yusuf Karimi | DeKalb | (404) 555-0144 | ykarimi@example.org | East metro Muslim community | Aunjanue Mosley | 3 |  | 2026-04-16 |  |  |  | 6 | Wants to host at masjid; needs childcare confirmation. | 2026-05-01
11 | Brittany Holland | Henry | (404) 555-0166 | bholland@example.org | McDonough Black women | Maria Palacios | 4 |  | 2026-04-20 | 2026-04-26 |  |  | 8 | Attended coalition retreat; ready to commit. | 2026-05-01
12 | Joseph Whitehorse | Muscogee | (706) 555-0129 | jwhitehorse@example.org | Columbus union + civic groups | ACLU-GA | 1 | [6 empty] | Identified by ACLU at April training. Needs first contact. | 2026-04-30

## Counties
Counties
Strategic frame: which GA counties we are organizing, why, and what is locked.
ID | County | Priority (1=lead, 3=stretch) | Why this county (cracking / packing / growth / vulnerable seat) | Target legislator(s) | Captain locked? (Yes/No) | Captain name(s) | Town hall date | Coalition partners on board | Status | Lead organizer (staff) | Notes
1 | Gwinnett | 1 | AAPI population doubled 2010 to 2020; cracked across 4 GA House districts in 2021 map; core of Section 2 protection if maps redrawn | Sen. Sally Harrell (SD-40), Rep. Sam Park (HD-107) | Yes | Aunjanue Mosley + Pastor J. Reed | 2026-06-06 | GA Familias Unidas, AAAJ-Atlanta, NAACP Gwinnett | Locked | Maria Palacios | AAPI community story is the lead.
2 | Fulton | 1 | Largest county in GA; concentration of Black voters; 2021 map split SW Fulton across 3 districts | Sen. Sonya Halpern (SD-39), Rep. Park Cannon (HD-58) | Yes | Tyrone Brooks Jr. | 2026-05-16 | ACLU-GA, NAACP-GA, NDWA-GA | Locked | Maria Palacios | Town hall already locked.
3 | DeKalb | 1 | Heavily Black; multiple state legislators on the fence on GA VRA Act 2026 | Sen. Tonya Anderson (SD-43), Rep. Saira Draper (HD-90) | No | Imam Yusuf Karimi (in progress) |  | GA Familias Unidas, faith coalition | 1:1 done | Maria Palacios | Karimi at stage 3; need to confirm venue.
4 | Cobb | 2 | Suburban swing; GA House districts trending; AAPI growth in northeast | Sen. Kay Kirkpatrick (SD-32), Rep. Mary Frances Williams (HD-37) | No | Kim Park (in progress) |  | AAAJ-Atlanta, ACLU-GA | Stalled | Linh Bui | Park skeptical; need written coalition commitment.
5 | Clayton | 1 | Most diverse county in GA; HD lines previously redrawn to dilute Latinx growth | Sen. Valencia Seay (SD-34), Rep. Sandra Scott (HD-76) | No | Esperanza Rivera (paused) |  | GA Familias Unidas, NAACP-Clayton | Paused | Maria Palacios | Rivera unavailable until 5/15.
6 | Henry | 2 | Rapid Black population growth; new HD-129 vulnerable to redrawing | Sen. Emanuel Jones (SD-10), Rep. El-Mahdi Holly (HD-116) | No | Brittany Holland (training) |  | NAACP-Henry | On track | Maria Palacios | Holland at stage 4; commit conversation booked 5/8.
7 | Chatham | 2 | Coastal; Black majority Savannah; vulnerable HD lines in Pooler corridor | Sen. Derek Mallow (SD-2), Rep. Edna Jackson (HD-165) | Yes | Rev. Sarah Womack | 2026-05-30 | Black Voters Matter Savannah, NAACP-Savannah | Locked | Maria Palacios | Strong faith infrastructure.
8 | Bibb | 2 | Macon Black political base; threatened by HD consolidation | Sen. David Lucas (SD-26), Rep. Miriam Paris (HD-142) | No | DeMarcus Allen (training) |  | ACLU-GA, Mercer student org | On track | Maria Palacios | Allen high capacity.
9 | Hall | 3 | Latinx growth (Gainesville); poultry industry workers; HD lines previously cracked | Sen. Shawn Still (SD-48), Rep. Emory Dunahoo (HD-31) | No | Carlos Mendez (contacted) |  | GA Familias Unidas | Stalled | Carlos Mendez (vol) | Awaiting reply.
10 | Muscogee | 3 | Columbus; military families; HD-137 swing | Sen. Ed Harbison (SD-15), Rep. Calvin Smyre seat (HD-135) | No | Joseph Whitehorse (identified) |  | ACLU-GA | Identified | ACLU-GA | First contact pending.
11 | Richmond | 3 | Augusta Black majority; 2021 map preserved but vulnerable | Sen. Harold Jones (SD-22), Rep. Mack Jackson (HD-128) | No |  |  | TBD | Open | Maria Palacios | Recruiting captain.

## Funnel
Recruitment funnel
Where each captain is in the journey from identified to hosting. Updates live from the Captains tab.
Stage | Count | Cumulative % | Drop-off | What we do at this stage
1. Identified |  |  |  | Build the list. Recruit from coalition partners, faith bodies, mutual aid networks.
2. Contacted |  |  |  | Personal outreach (call, not email). Set the 1:1.
3. 1:1 done |  |  |  | 1-hour 1:1. Story of self / story of us / what would it take. Capture concerns.
4. Trained |  |  |  | 4-hour training: theory, run-of-show, accountability ask, de-escalation.
5. Committed |  |  |  | Signed onboarding + commitment. County assigned. Press kit handed off.
6. Hosting |  |  |  | Town hall locked. Date set. Captain leads from the front.

## Onboarding
County Captain Commitment
Print one per captain. Sign together at the end of the training.
A county captain leads the organizing of one town hall in 2026 to hold a Georgia state legislator publicly accountable on racialized maps and the Georgia Voting Rights Act of 2026. The work is relational; the goal is durable power, not one good event.
WHO I AM
Name
County
Phone + email
Constituency I am rooted in | e.g., Gwinnett AAPI faith leaders
Why I said yes (1 to 2 sentences)
WHAT I AM COMMITTING TO
Hours per week (average) | e.g., 6 to 8
Through what date | e.g., through November 5, 2026 election
Town hall date I am leading
Co-captain (if any) | Sharing load is a strength, not a weakness.
WHAT THE COALITION COMMITS TO ME
Lead staff organizer | Name + phone. They have my back.
Training provided | 4-hour captain training; story coaching round 1 + 2; run-of-show rehearsal.
Resources provided | Press kit; turnout templates; childcare + interpretation budget; legal observer; printing.
Decision-making seat | I have a vote in coalition meetings on my county’s plan.
Repair commitment | If we cause harm, we name it and repair publicly. We do not perform fixes.
BOUNDARIES + CARE
My non-negotiables | Things I will not do. Be specific.
My access needs | ASL, language, childcare, mental health, transportation, etc.
My check-in cadence | Weekly with lead organizer; biweekly with full coalition.
If I need to step back | Notice we owe each other (recommended: 2 weeks). Successor plan.
DISSENT + DISAGREEMENT
How I will surface dissent in meetings | Speak in the meeting; if not safe, name it 1:1 with lead organizer same day.
How I will receive dissent | Treat the least excited voice as data, not opposition.
If I disagree with a coalition decision | I follow the decision through this town hall; I bring the disagreement to the next coalition meeting.
SIGNATURES
Captain signature + date
Lead staff organizer signature + date
Coalition co-signer (most-impacted leader, not staff)

## Decision Log
Decision Log
Every coalition decision: who decided, what dissent was surfaced, what trade-off we accepted, when we will revisit.
ID | Date | Decision (one sentence) | Who decided | Who was in the room | Most-impacted voice present? | Dissent surfaced (verbatim) | Trade-off accepted | Revisit by
1 | 2026-04-12 | Adopt Public Narrative as primary theory; braid in power-based accountability for the legislator ask. | Coalition steering (5 votes) | Maria Palacios, Aunjanue Mosley, Pastor J. Reed, Linh Bui, Tyrone Brooks Jr. | Yes | Pastor Reed: “I worry confrontation will scare seniors who already do not feel safe at the Capitol.” | Use story-led format; accountability ask is the closing 10 minutes, not the spine. | 2026-05-30
2 | 2026-04-19 | Prioritize 8 counties for 2026 (Gwinnett, Fulton, DeKalb, Cobb, Clayton, Henry, Chatham, Bibb). | Coalition steering | Same as above + DeMarcus Allen, Rev. Womack | Yes | Linh Bui: “Muscogee + Hall need to be on the list; Latinx + military families are also at risk.” | Add Hall + Muscogee as stretch (priority 3) for late 2026; commit to 2 in 2027 cycle. | 2026-09-01
3 | 2026-04-26 | Lock $32k for interpretation + childcare across 8 town halls. | Maria Palacios + budget cmte | Maria Palacios, board treasurer, GA Familias Unidas | No (board treasurer is staff) | GA Familias Unidas: “Childcare line item too low for Clayton + Hall; 1 worker for 30 kids is not safe.” | Increase childcare from $8k to $12k; reduce printing budget by $4k; go digital where possible. | 2026-06-15